## Sheet1
Lifecycle Model Capability | Code and Fix | Waterfall | Evolutionary | Spiral | COTS Integration | Agile Development | MinimumExpected Capability
Works with ambiguous requirements | Poor | Poor | Fair-Excellent | Excellent | Excellent | Excellent | Poor
Works with ambiguous architecture | Poor | Poor | Poor | Excellent | Poor-Excellent | Excellent | Poor
Produces highly reliable system | Poor | Excellent | Fair-Excellent | Excellent | Poor-Excellent | Poor-Excellent | Excellent
Produces system with large growth potential | Poor | Excellent | Excellent | Excellent | N/A | Fair | Fair
Manages risks | Poor | Poor | Fair | Excellent | N/A | Fair | Excellent
Can be constrained to predefined schedule | Poor | Fair | Fair | Fair | Excellent | Poor | Excellent
Minimal management/technical oversight | Excellent | Poor | Fair | Fair | Excellent | Fair | Fair
Allows for midcourse correctoins | Poor-Excellent | Poor | Fair-Excellent | Fair | Poor | Excellent | Poor
Provides customer with progress visibility | Fair | Poor | Excellent | Excellent | N/A | Excellent | Excellent
Provides management with progress visibility | Poor | Fair | Excellent | Excellent | N/A | Excellent | Excellent
Requires little manager or developer sophistication | Excellent | Fair | Fair | Poor | Fair | Fair | Fair